## Sheet1
|  | Project Name: | IMS- Inventroy Managment System
|  | Project Description: | Application to manage Customers,Items and Orders
|  | Project Owner: | Waleed Tahir
Risk ID | Date registered | Risk area | Risk description | Probability |  |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 18.12.20 | covid-19 | Potential for me or someone in my immediate proximity to contract the virus and cause me to be both unwell and in a state of lockdown |  |  | x |  | x |  | Impact on my workrate as a result of being ill or having to take care of someone who is ill | Ongoing | Wash hands and hand santise regularily as well as follwing the latest government guidlines to minimize the potential risk of encountering teh virus in teh first place.
2 | 18.12.20 | Damage to laptop | Potential of my laptop to be damaged either physically from something liek a drop or from a software perscective | x |  |  |  |  | x | would leave me unable to continue working until a replacement could be sorted | 1 week | Maintain good practice in teh upkeeo and storage of my laptop as well as ensuring a clean working environment e.g. no nearby drinks
3 | 27/12/20 | Lack of technocal knowledge | New to coding and so I have limited experfience working with language logic and more complex coding problems. | x |  |  |  | x |  | Will inevitably slow my progress down putting more pressure on the completion time of the project | Ongoing | Rely on the resources provided to me as well as consolidating my learning as I progress.
4 | 2021-07-01 | Schedule managment | Exceeding the neccesary time constraints |  | x |  |  | x |  | will mean that I do not have a complete build on the day of my presentation | ongoing | Manage time effectivly using supporting tools such as Jira board
5
6
7
8
9
10